## Sheet1
Tasks | Tables | Expected Start Date | Start Date | End Date | Status | Form Load | Help File | AutoNumber | Deletion in Grid | Save | Date | Teacher's Remarks
Demand Note | DN, DNDetail | 2014-10-10 | 2014-10-10 | 2014-10-18 | Completed & Revised | Done | Done | Done |  | Done |  | DN = Master Level and DNDetail=Detail Level Table
Gate Inword | GateInword, GateInwordDetail | 2014-10-11 | 2014-10-11 | 2014-10-12 | Completed & Revised | Done | Done | Done | Done | Done
Finish Item Receive | FinishRec, FinRec, FinishRecDetail | 2014-10-22 | 2014-10-22 | 2014-10-22 | Completed & Revised | Done | Done | Excluded |  | Done |  | FinishRec = Upper Grid, FinRec= Master Level, FinishRecDetail= Detail Table
Delivery Order | Do_Det, Do_Hist, Item_Sec, Ledger | 2014-10-14 | 2014-10-14 | 2014-10-22 | Completed & Revised | Done | Done | Done |  | Done
Invoice Entry | Inv_Det, Inv_Hist, Ledger | 2014-10-25 | 2014-10-25 | 2014-10-26 | Completed | Done | Done | Done |  | Done
Invoice Entry (CF) | PLEASE SPECIFY TABLES | [6 empty] | Excluded
Sale Return Entry | InvR_Det, InvR_Hist, Ledger | 2014-10-25 | 2014-10-25 | 2014-10-26 | Completed | Done | Done | Done |  | Done
Item Code Description | Item | 2014-10-26 | 2014-11-25 | 2014-12-01 | Completed | Done | Done | Done |  | Done
Issue Return | IssueRet, IssueRetDetail, Item_Sec | 2014-10-27 | 2014-10-27 | 2014-10-28 | Completed | Done | Done | Done |  | Done
Packing Formula Definition | PackFormula, PackFormulaDetail | 2014-10-28 | 2014-10-29 | 2014-10-30 | Completed & Revised | Done | Done | Excluded |  | Done
Formula Definition | Formula, FormulaDetail | 2014-10-31 | 2014-10-31 | 2014-10-31 | Completed & Revised | Done | Done | Excluded |  | Done
Sale Order Entry | Ord_Hist, Ord_Det | 2014-10-31 |  |  | Completed & Revised | Done | Done | Done |  | Done
Change from ASCII to english (For Item Code Des) |  | 2014-01-17 |  |  | Completed & Revised | Done | Done | Done |  | Done